GHANA EXTRACTIVE INDUSTRIES TRANSPARENCY INITIATIVE (GHEITI)

2010 - 2012 WORK PLAN

| OBJECTIVE 1: CARRY OUT AN INDEPENDENT AUDIT OF EXTRACTIVE SECTOR PAYMENTS AND BENEFITS |
| --- |
| Output | Activity | Start Date | End Date | Amount ($) | Source of Funding | Responsibility | Expected Outcome |
| Production of 2006, 2007 and 2008 EITI Reports | GHEITI Aggregator to collect, reconcile and aggregate data | January | End of June 2010 | 179,214 | EITI Grant/GoG | GHEITI Secretariat/GHEITI Aggregator | 2006, 2007, 2008 Aggregators reports produced |
| Round table to discuss the final EITI Reports organized | Organize workshop to validate and discuss the recommendation s of the EITI Reports | June, 2010 | End of June 2010 | 20,000 | GoG | GHEITI Secretariat/NSC | EITI 2006 -2008 Reports Validated |
| Process of Production of 2009 EITI reports initiated | Engage an Aggregator | Oct. 2010 | Dec. 2010 |  |  | GHEITI Secretariat/GHEITI Aggregator | Aggregator appointed/reappo-inted |
| Production of 2009 EITI reports | GHEITI Aggregator to collect, reconcile and aggregate data | Jan. 2011 | March 2011 | 60,000 | GoG | GHEITI Secretariat/GHEITI Aggregator | 2009 EITI Reports produced |
| Round table to discuss the final EITI 2009 reports | Organize workshop to validate and discuss the recommendation of the EITI report | April, 2011 | End of April, 2011 | 20,000 | GoG | GHEITI Secretariat/Aggregator/NSC | 2009 EITI reports Validated |
| Process of production of 2010 EITI reports initiated | Engage an Aggregator | Oct. 2011 | Dec. 2011 |  |  | GHEITI Secretariat/NSC | Aggregator appointed/reappointed |
| Production of 2010 EITI reports | GHEITI Aggregator to collect, reconcile and aggregate data | Jan 2012 | March 2012 | 60,000 | GoG | GHEITI Secretariat/GHEITI Aggregator | 2010 EITI reports produced |
| Round table to discuss the final EITI 2010 reports | Organize a workshop to validate and discuss the recommendation of the EITI report | April 2012 | End of April 2012 | 20,000 | GoG | GHEITI Secretariat/Aggregator/NSC | 2009 EITI reports Validated |
| Process of production of 2011 EITI reports to include oil and gas initiated | Engage an Aggregator | August 2012 | Sept. 2012 |  |  | GHEITI Secretariat/NSC | Aggregator appointed |
| Production of 2011 EITI reports to include oil and gas | GHEITI Aggregator to collect, reconcile and aggregate data | Oct, 2012 | Dec, 2012 | 80,000 | WB-TF | GHEITI Secretariat/GHEITI Aggregator | 2012 EITI reports produced |
| Sub-Total A |  |  |  | 439,214 |  |  |  |
| OBJECTIVE 2: EXTENSION OF GHANA EITI TO THE OIL, GAS AND FORESTRY SECTOR |
| Cabinet memorandum for the extension of GHEITI to oil and gas sector developed | Preparation of the joint cabinet memorandum | January, 2010 | March 2010 |  |  | GHEITI Secretariat/NSC/MoEn/MoFEP/MLNR | The extension approved by Cabinet |
| GHEITI National EITI Steering Committee expanded to include the oil and gas sector | Inauguration of expanded NSC to cover oil and gas | April, 2010 | End of April 2010 |  |  | GHEITI Secretariat/NSC/MoEn | An new Ghana EITI NSC inaugurated |
| Reporting Templates for the oil and gas sector developed by NSC | Organize a retreat for NSC to develop oil and gas reporting templates | May, 2010 | End of May 2010 | 20,000 | GoG | GHEITI Secretariat/NSC | Draft oil and gas reporting template developed |
| Consultation workshop on extending GHEITI to the oil/gas sector for relevant MDAs organized | Organize stakeholder workshop on extending GHEITI to the oil and gas sector for relevant MDAs | October, 2010 | End of October. 2010 | 40,000 | GTZ | GHEITI Secretariat/NSC | Consensus reached |
| Consultation workshop on extending GHEITI to the oil/gas sector for Communities in the oil catchment area organized | Organize stakeholder workshop on extending GHEITI to the oil and gas sector for Communities in the oil catchment area | Nov.2010 | End of Nov.2010 | 20,000 | WB-TF | GHEITI Secretariat/NSC | Consensus reached |
| Consultation workshop on extending GHEITI to the oil/gas sector for CSOs and NGOs organized | Organize stakeholder workshop on extending GHEITI to the oil and gas sector for CSOs and NGOs | Dec, 2010 | End of Dec. 2010 | 20,000 | WB-TF | GHEITI Secretariat/NSC | Consensus reached |
| Consultation workshop on extending GHEITI to the oil/gas sector for oil companies organized | Organize stakeholder workshop on extending GHEITI to the oil/gas sector for oil companies | January 2011 | End of January 2011 | 40,000 | GTZ | GHEITI Secretariat/NSC | Consensus reached |
| Process of extension of GHEITI to the forestry sector initiated | Engage a Consultant to Undertake a scoping of the Extension to the forestry Sector | Feb. 2011 | End of March.2011 | 25,000 | GTZ | GHEITI Secretariat/GHEITI NSC | Scoping exercise into the forestry sector undertaken |
| Stakeholder Consultation workshop on extension of GHEITI to the forestry sector organized | Organize stakeholder consultation workshop on extension of GHEITI to the forestry sector | August 2011 | End of August 2011 | 25,000 | WB-TF | GHEITI Secretariat/NSC | Consensus reached |
| Sub-Total B |  |  |  | 190,000 |  |  |  |
| OBJECTIVE 3: PUBLICATION AND DISSEMINATION OF EITI AUDIT REPORTS |
| Press Conference organized | Organize Press Conference to launch the 2006,2007 & 2008 EITI Audit Reports | July | End July, 2010 | 10,000 | GoG | GHEITI Secretariat/NSC | Ghana EITI Audit Reports launched |
| Printing of EITI Audit report for 2006, 2007 and 2008 | Printing of EITI Audit reports for 2006, 2007 and 2008 | End of July | Mid September, 2010 | 10,000 | WB-TF | GHEITI Secretariat/NSC | EITI reports printed |
| EITI Audit Report dissemination workshop for District Assemblies in the mining area organized | Organize dissemination workshop of EITI Aggregators reports for 2006, 2007, 2008 in Tarkwa | Aug 2010 | End of Aug 2010 | 20,000 | WB-TF | GHEITI Secretariat/NSC | District Assemblies well informed on EITI reports |
| EITI Audit Reports published in the Daily News papers | Publication of EITI Audit Reports for 2006, 2007 and 2008 in the Daily News papers | Sept 2010 | End of Sept, 2010 | 10,000 | GTZ | GHEITI Secretariat | EITI Audit Reports published |
| EITI Audit Report dissemination workshop for CSOs organized | Organize EITI dissemination workshop of Aggregators reports for 2006, 2007, 2008 in Kumasi/Obuasi | Sept 2010 | End of Sept. 2010 | 20,000 | WB-TF | GHEITI Secretariat/NSC | CSOs well informed on EITI reports |
| EITI Audit Report dissemination workshop for the Media organized | Organize EITI dissemination workshop of Aggregators reports for 2006, 2007, 2008 in Sunyani | February 2011 | End of Feb 2011 | 20,000 | WB-TF | GHEITI Secretariat/NSC | media well informed on EITI reports |
| EITI Audit Report dissemination workshop for relevant Government Agencies organized | Organize EITI dissemination workshop of Aggregators reports for 2006, 2007, 2008 in Accra | March 2011 | End of March, 2011 | 20,000 | WB-TF | GHEITI Secretariat/NSC | Government Agencies well informed on EITI reports |
| EITI Audit Report dissemination workshop for Mining Companies organized | Organize EITI dissemination workshop of Aggregators reports for 2006, 2007, 2008 in Tarkoradi | May 2011 | End of May 2011 | 20,000 | WB-TF | GHEITI Secretariat/NSC | Mining Companies/District Assemblies well informed on EITI reports |
| 2009 EITI Audit Report Launched | Organize press conference to launch 2009 EITI Audit reports | June 2011 | End of June 2011 | 10,000 | GoG | GHEITI Secretariat/NSC | Ghana EITI Audit reports launched |
| 2009 EITI Audit reports published in the Daily News papers | Publication of 2009 EITI Audit reports in the Daily News papers | July 2011 | End of July 2011 | 10,000 | GTZ | GHEITI Secretariat | 2009 EITI Audit reports published |
| EITI 2009 Audit Report dissemination workshop for relevant MDAs organized | Organize EITI dissemination workshop of 2009 Aggregators reports Tarkoradi | Sept 2011 | End of Sept. 2011 | 25,000 | WB-TF | GHEITI Secretariat/NSC | Relevant MDAs well informed on EITI report. |
| EITI 2009 Audit Report dissemination workshop for CSOs organized | Organize EITI dissemination workshop of 2009 Aggregators report in Kumasi | Nov. 2011 | End of Nov. 2011 | 25,000 | WB-TF | GHEITI Secretariat/NSC | CSOs well informed on EITI reports |
| EITI 2009 Audit Report dissemination workshop for the mining companies/District Assemblies organized | Organize EITI dissemination workshop of 2009 Aggregators report in Tarkwa | Dec. 2011 | End of Dec. 2011 | 25,000 | WB-TF | GHEITI Secretariat/NSC | Mining companies/District Assemblies well informed on EITI reports |
| Press Conference organized | Organize Press Conference to launch the 2010 EITI Audit Reports | May | End May, 2012 | 10,000 | GoG | GHEITI Secretariat/NSC | Ghana EITI Audit Reports launched |
| EITI 2010 audit report published in the daily news papers | Publication of 2010 EITI audit reports in the daily news papers | June 2012 | End of June 2012 | 10,000 | GoG | GHEITI Secretariat | 2010 EITI audit reports published |
| EITI 2010 Audit Report dissemination workshop for the relevant MDAs organized | Organize EITI dissemination workshop of 2010 Aggregators report in Accra | June. 2012 | End of June. 2012 | 25,000 | WB-TF | GHEITI Secretariat/NSC | Relevant MDAs well informed on EITI reports |
| EITI 2010 Audit Report dissemination workshop for the CSOs organized | Organize EITI dissemination workshop of 2010 Aggregators report in Kumasi | July. 2012 | End of July. 2012 | 25,000 | WB-TF | GHEITI Secretariat/NSC | CSOs well informed on EITI reports |
| EITI 2010 Audit Report dissemination workshop for the Mining Companies/District Assemblies organized | Organize EITI dissemination workshop of 2010 Aggregators report in Tarkwa | Aug. 2012 | End of Aug. 2012 | 25,000 | WB-TF | GHEITI Secretariat/NSC | Mining Companies and District Assemblies well informed on EITI reports |
| Sub-Total C |  |  |  | 320,000 |  |  |  |
| OBJECTIVE 4: SENSITIZATION AND AWARENESS CREATION OF GHANA EITI |
| Sensitization workshop on Ghana EITI for Parliamentarians in Accra organized | Organize Sensitization workshop for the Parliamentarians in Accra | March 2010 | March 2010 | 20,000 | GTZ | GHEITI Secretariat/NSC | Parliamentarians well sensitized |
| Sensitization on oil and gas and Validation of draft oil and gas reporting templates workshop for relevant MDAs organized | Organize Sensitization workshop on oil and gas and Validate oil and gas reporting templates in Accra | April 2010 | End of April 2010 | 20,000 | GoG | GHEITI Secretariat/NSC | Relevant MDAs well sensitized and Reporting Template validated |
| Sensitization on oil and gas and Validation of draft oil and gas reporting templates report workshop for District Assemblies, media and CSOs organized | Organize sensitization workshop on oil and gas and Validate oil and gas reporting templates in the Western Region (Tarkoradi, Cape Three points and Half Assini) | May 2010 | End of May 2010 | 25,000 | GTZ | GHEITI Secretariat/NSC | District Assemblies, CSOs and media well sensitized and Reporting Template Validated |
| Validation report dissemination workshop for the media organized | Organize workshop to disseminate validation reports in Accra | June 2010 | End of June 2010 | 20,000 | WB-TF | GHEITI Secretariat/NSC | Media well sensitized on validation report |
| Validation report dissemination workshop for Government Agencies organized | Organize workshop to Disseminate validation reports in Accra | July 2010 | End of July 2010 | 20,000 | WB-TF | GHEITI Secretariat/NSC | Government Agencies well sensitized on validation report |
| Sub-Total D |  |  |  | 105,000 |  |  |  |
| OBJECTIVE 5: COMMUNICATING GHANA EITI |
| Sensitization workshop for the media organized | Organize sensitization workshop for the media in Accra | January 2011 | End January 2011 | 25, 000 | GTZ | GHEITI Secretariat/NSC | GHEITI well communicated to the media |
| GHEITI week organized | Organize a GHEITI week | July 2011 | End of July 2011 | 40,000 | GTZ | GHEITI Secretariat/NSC | GHEITI well communicated to the public |
| Video documentary on GHEITI with local translations produced | Produce and telecast a video documentary on national television | Aug. 2011 | End of Sep. 2011 | 10,000 | GTZ | GHEITI Secretariat/NSC | GHEITI well communicated to the public |
| Radio talk shows on GHEITI organized | Organized radio talk shows to disseminate information on GHEITI | Oct. 2011 | End of Nov. 2011 | 10,000 | GoG | GHEITI Secretariat/NSC | GHEITI well communicated to the public |
| Publication of EITI newsletters | Production of quarterly newsletters on GHEITI | Jan,2010 | Dec.2012 | 25,000 | GTZ | GHEITI Secretariat/NSC | GHEITI well communicated to the public |
| Public forums on GHEITI organized | Organize public forums in all the regional capitals | March 2012 | End of April. 2012 | 40,000 | WB-TF | GHEITI Secretariat/NSC | GHEITI well communicated to the public |
| GHEITI Road show organized | Organize GHEITI road show throughout the country | Sept 2012 | End of Oct. 2012 | 50,000 | WB-TF | GHEITI Secretariat/NSC | GHEITI well communicated to public |
| Sub-Total E |  |  |  | 200,000 |  |  |  |
| OBJECTIVE 6: LEGISLATION OF GHANA EITI |
| Framework Act to legislate Ghana EITI developed | Engage a consultant to draft the EITI Act | Sept. 2010 | End Nov.2010 | 15,000 | GTZ | GHEITI Secretariat/NSC | GHEITI Legislated |
| A Monitoring and Evaluation Strategy Plan for GHEITI developed | Hire a Consultant to develop a Monitoring and Evaluation Action Plan | Jan. 2011 | March 2011 | 20,000 | GoG | GHEITI Secretariat/NSC | M & E Action Plan developed. Internal Evaluation of Ghana EITI |
| Monitoring and Evaluation of Ghana EITI undertaken | Undertake a Monitoring and Evaluation of the Ghana EITI | Aug. 2011 | Sept. 2011 | 25,000 | WB-TF | GHEITI Secretariat/NSC/Consultant | M & E of the Ghana EITI undertaken |
| Sub-Total F |  |  |  | 60,000 |  |  |  |
| OBJECTIVE 7: CAPACITY BUILDING AND INSTITUTIONAL STRENGTHENING |
| Capacity building for NSC and GHEITI Secretariat members on oil and gas carried out | Invite International facilitators from Nigeria and Cameroon | May 2010 | End of July, 2010 | 40,000 | GTZ | GHEITI Secretariat/NSC | Well informed team |
| Capacity building for key EITI members on oil and gas EITI | Four (4) short Int. courses and seminars yearly | January 2010 | End of December 2012 | 50,000 | WB-TF | GHEITI Secretariat/NSC | Well informed team |
| Capacity Building for key NSC members | 3 delegates to participate in International EITI Conference and other relevant Conferences yearly | January 2010 | December 2012 | 50,000 | GTZ | GHEITI Secretariat/NSC | Well informed team |
| Capacity building for NSC members in the Oil/ Gas Sector | Study tour for 6 NSC members to Azerbaijan | January 2010 | December 2010 | 60,000 | GTZ | GHEITI Secretariat/NSC | Well informed team |
| Capacity building and training workshop for District Assemblies on oil and gas organized | Organize capacity building and training workshop for District Assemblies in Tarkwa | Jan 2012 | End Jan. 2012 | 25,000 | WB-TF | GHEITI Secretariat/NSC | District Assemblies well informed |
| Capacity building and training workshop for CSOs on oil and gas organized | Organize capacity building and training workshop for CSOs in Tarkoradi | Feb.2012 | End Feb 2012 | 25, 000 | GTZ | GHEITI Secretariat/NSC | CSOs well informed |
| Capacity building and training workshop for media on oil and gas organized | Organize capacity building and training workshop for the media in Kumasi | May. 2012 | End of May 2012 | 25,000 | WB-TF | GHEITI Secretariat/NSC | Media well informed |
| Capacity building and training workshop for oil and gas companies organized | Organize capacity building and training workshop for the oil and gas companies | Aug. 2012 | End of Aug. 2012 | 20,000 | WB-TF | GHEITI Secretariat/NSC | Oil and gas companies well informed |
| GHEITI Information centre established in Tarkwa and Obuasi | Rental of office space and furnishing with logistics and equipments | January 2010 | December 2012 | 80,000 | WB-TF | GHEITI Secretariat/NSC | Information centre established |
| Ghana EITI Secretariat refurbished | Refurbishment of the Ghana EITI Secretariat (two room office space) | March 2010 | December 2010 | 40,000 | GTZ | GHEITI Secretariat | Ghana EITI Secretariat refurbished |
| GHEITI Secretariat well strengthened | Provision of logistics and equipments: computers, laptops, printers, wireless internet modems, scanners, projectors etc | January 2010 | December 2012 | 80,000 | GTZ | GHEITI Secretariat | Well equipped Secretariat |
| Sub-Total G |  |  |  | 495,000 |  |  |  |
| OBJECTIVE 8: GHEITI NATIONAL STEERING COMMITTEE (NSC) MEETINGS |
| NSC meeting to discuss GHEITI Validation draft report organized | Organized GHEITI NSC meeting to discuss GHEITI draft Validation report | January 2010 | 15th January 2010 | 5,000 | GoG | GHEITI Secretariat | Draft final Validation report |
| NSC Meeting to discuss GHEITI Validation Draft Final Report organized | Organize GHEITI NSC to discuss GHEITI draft final Validation report | 01 Feb | 07 Feb | 5,000 | GoG | GHEITI NSC/SEC. | Final Validation report |
| GHEITI NSC meeting organized | Organize GHEITI NSC meeting once every quarter | March 2010 | End of Dec 2012 | 60,000 | GoG | GHEITI Secretariat/NSC | Progress of GHEITI implementation |
| Sub-Total H |  |  |  | 70,000 |  |  |  |
| GRAND TOTAL |  |  |  | 1,879,214 |  |  |  |

TOTAL GOG -$360,000

TOTAL GTZ- $580,000

TOTAL WORLD BANK - $760,000