REVISED DRAFT WORK PROGRAMME FOR A PILOT PROJECT IN COMMODITY TRADING

1.0 Introduction

Ghana has been selected as one of the few countries to undertake a pilot project in commodity trading.

The EITI Requirement 4.2 states that where the sale of the state’s share of production or other revenues collected in-kind is material, the government, including state-owned enterprises; are required to disclose the volumes sold and revenues received. The published data must be disaggregated by individual company and to levels commensurate with the reporting of other payments and revenue streams as required by requirement 4.7.

2.0 Objectives of the pilot project

The objectives of the pilot is to help EITI implementing countries with significant commodity trading activities to deal with EITI requirements related to disclosure on such transactions which include:

- gaining a good understanding of the mandate of the government agency or SOE in selling commodities on behalf of the state or the private sector players in mining;

- identifying the key actors and transactions involved in commodity trading for mining and oil/gas;

- developing a framework for disclosure of timely and reliable information on commodity by both private sector and SOEs ; and

- ensuring adequate reporting in accordance with the relevant EITI requirements (Requirement 4.2 ).

3.0 Scope of the pilot

The Ghana EITI has agreed to expand the scope of the pilot beyond the national oil company to include private sector players in the extractives sector.  This is to allow for comparison between the achieved prices of private sector companies with those of SOEs, with a view to promoting transparency in these transactions.

The project is, therefore, expected to address reporting on both sales of in-kind revenues in the oil/gas sector and sales by mining companies which include reporting by the type of product, price, market and sales volume.

3.1 Key output of the pilot would be as follows:

- Commodity trading reports on Ghana to bring further transparency to commodity trading by SOEs and private companies;

- Model reporting templates; and

- An evaluation report on the main findings of the pilot, including lessons learnt and recommendations.

| S/N | ACTIVITY | TIMELINE | AMOUNT (US$) | EXPECTED OUTPUT |
| --- | --- | --- | --- | --- |
| 1. | Constitute a Working Group with clear TOR by the MSG to periodically update the MSG | April, 2017 | - | Consensus meeting report on technical issues agreed on by the stakeholders |
| 2. | Organise capacity building workshop for GHEITI Sec./MSG on commodity trading in mining and oil/gas sectors | June, 2017 | 15,000 |  |
| 3. | Organise a technical round table for key stakeholders to discuss key issues on commodity trading in mining & oil and gas sectors | June, 20172017 | 30,000 | MSG/GHEITI Secretariat staff trained on commodity trading issues in mining and oil/gas |
| 4. | Develop ToR and reporting templates for commodity trading in mining and oil/gas | July, 2017, 2017 | - | ToR and reporting templates developed |
| 5. | Undertake stakeholder inception/orientation workshop to discuss their roles and for them to understand how to complete the reporting templates | July, 2017 | 15,000 | Stakeholders orientation/inception workshop undertaken to understand their roles and how to complete the templates |
| 6. | Undertake a reconciliation exercise on commodity trading in mining and oil/gas sectors Advertise the expression of Interest in the dailies Procure a consultant to undertake the reconciliation exercise on commodity trading | July, 2017 July, 2017 July, 2017 | 46,000 6,000 40,000 | Consultant engaged to undertake the scoping study Expression of Interest advertised Consultant procured |
| 7. | Submission of an inception report | August, 2017 | - | Inception report submitted and discussed by MSG |
| 8. | Submission of final draft report | September, 2017 |  | Final report submitted in hardcopy and soft copy versions. |
| 9. | Printing of commodity trading report for mining and oil/gas sectors | September, 2017 | 10,000 | Commodity trading report produced |
| 10. | Organise stakeholder validation workshop to discuss the final draft report | October, 2017 | 20,000 | Report on draft commodity trading validation workshop |
| 11. | Organise a workshop to launch the report | October, 2017 | 20,000 | Commodity trading Report launched |
| 12. | Organise 3 zonal stakeholder dissemination workshops for the northern, middle and southern belts on the findings and recommendations of the report | November, 2017 | 100,000 | Public well informed on findings and recommendations |
|  | Total |  | 256,000 |  |